## 9 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date
9 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Define purpose of event and target audience
#VALUE! | Decide on event format
#VALUE! | Conduct site visits
#VALUE! | Create and maintain event budget
#VALUE! | Confirm date and venue
#VALUE! | Secure speakers, entertainment, president, https://rockpride.sru.edu/forms/presidentialrequest/
#VALUE! | Determine method of communicating event - (e-mail, direct mail, advertisment). Contact University Communications or Advancement
#VALUE! | Begin to gather data necessary for invitations
#VALUE! | Request catering proposals from ARAMARK
#VALUE! | Begin creating event materials
#VALUE! | Determine AV, tables, chairs, linens, china, small games license etc.
#VALUE! | Finalize guest list
#VALUE! | Request rental quotes, if needed
#VALUE! | Finalize text and design for event materials
#VALUE! | Mail "save the date" cards
#VALUE! | Revisit venue to determine preferred room layout, traffic flow, and color themes
#VALUE! | Request food tasting
#VALUE! | Update mailing list from any returns on "save the date" mailing. Share updates with Alumni & Advancement
#VALUE! | Hire a florist, if needed/determine centerpieces
#VALUE! | Final approval of invitation
#VALUE! | Notify police if spaces need blocked off
#VALUE! | Send invitations
#VALUE! | Create and maintain RSVP report
#VALUE! | Finalize menu and all rental contracts
#VALUE! | Select/order event giveaways
#VALUE! | Organize RSVPs
#VALUE! | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
#VALUE! | Request security, if needed
#VALUE! | Submit work orders
#VALUE! | Finalize programs
9 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Create Campus Event Briefing, required if President is attending. Share with Troy Miller
#VALUE! | Create information for volunteers and staff working event
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements, pay invoices
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want toremember next time
POST EVENT | Provide Advancement guest list

## 6 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date - M-D-YYYY | 2025-07-01
6 Month Plan | Task | Actual Date Completed | Comments
2025-01-02 | Define pourpose of event and target audience
2025-01-02 | Decide on event format
2025-01-02 | Conduct site visits
2025-02-01 | Create and maintain event budget
2025-02-01 | Confirm date and venue
2025-02-01 | Secure speakers, entertainment, president, https://rockpride.sru.edu/forms/presidentialrequest/
2025-02-01 | Determine method of communicating event - (e-mail, direct mail, advertisment). Contact University Communications or Advancement
2025-02-01 | Begin to gather data necessary for invitations
2025-02-01 | Request catering proposals from ARAMARK
2025-03-03 | Begin creating event materials
2025-04-02 | Determine AV, tables, chairs, linens, china, small games license etc.
2025-04-02 | Finalize guest list
2025-04-02 | Request rental quotes, if needed
2025-04-02 | Finalize text and design for event materials
2025-04-02 | Mail "save the date" cards
2025-04-02 | Revisit venue to determine preferred room layout, traffic flow, and color themes
2025-05-02 | Request food tasting
2025-05-02 | Update mailing list from any returns on "save the date" mailing. Share updates with Alumni & Advancement
2025-05-02 | Hire a florist, if needed/determine centerpieces
2025-05-02 | Final approval of invitation
2025-05-02 | Notify police if spaces need blocked off
2025-05-20 | Send invitations
2025-05-20 | Create and maintain RSVP report
2025-06-01 | Finalize menu and all rental contracts
2025-06-01 | Select/order event giveaways
2025-06-01 | Organize RSVPs
6 Month Plan | Task | Actual Date Completed | Comments
2025-06-01 | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy emails to those that will be attending
2025-06-01 | Request security, if needed
2025-06-01 | Submit work orders
2025-06-10 | Finalize programs
2025-06-17 | Create Campus Event Briefing, required if President is attending. Share with Troy Miller
#VALUE! | Create information for volunteers and staff working event
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements, pay invoices
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want to remember next time
POST EVENT | Provide Advancement guest list

## 3 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date
3 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Define purpose of event and target audience
#VALUE! | Decide on event format
#VALUE! | Conduct site visits
#VALUE! | Create and maintain event budget
#VALUE! | Confirm date and venue
#VALUE! | Secure speakers, entertainment, president, https://rockpride.sru.edu/forms/presidentialrequest/
#VALUE! | Determine method of communicating event - (e-mail, direct mail, advertisment). Contact University Communications or Advancement
#VALUE! | Begin to gather data necessary for invitations
#VALUE! | Request catering proposals from ARAMARK
#VALUE! | Begin creating event materials
#VALUE! | Determine AV, tables, chairs, linens, china, small games license etc.
#VALUE! | Finalize guest list
#VALUE! | Request rental quotes, if needed
#VALUE! | Finalize text and design for event materials
#VALUE! | Mail "save the date" cards
#VALUE! | Revisit venue to determine preferred room layout, traffic flow, and color themes
#VALUE! | Request food tasting
#VALUE! | Update mailing list from any returns on "save the date" mailing. Share updates with Alumni & Advancement
#VALUE! | Hire a florist, if needed/determine centerpieces
#VALUE! | Final approval of invitation
#VALUE! | Notify police if spaces need blocked off
#VALUE! | Send invitations
#VALUE! | Create and maintain RSVP report
#VALUE! | Finalize menu and all rental contracts
#VALUE! | Select/order event giveaways
#VALUE! | Organize RSVPs
3 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy emails to those that will be attending
#VALUE! | Request security, if needed
#VALUE! | Submit work orders
#VALUE! | Finalize programs
#VALUE! | Create Campus Event Briefing, required if President is attending
-14 | Create information for volunteers and staff working event
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement
POST EVENT | Make notes about vendors that you might want to remember next time
POST EVENT | Provide Advancement guest list

## 1 Month Plan
Host
Client
Event Date/Time
Event Coordinator
Location
Event Date
1 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Define purpose of event and target audience
#VALUE! | Decide on event format
#VALUE! | Conduct site visits
#VALUE! | Create and maintain event budget
#VALUE! | Confirm date and venue
#VALUE! | Secure speakers, entertainment, president, https://rockpride.sru.edu/forms/presidentialrequest/
#VALUE! | Determine method of communicating event - (e-mail, direct mail, advertisment). Contact University Communications or Advancement
#VALUE! | Begin to gather data necessary for invitations
#VALUE! | Request catering proposals from ARAMARK
#VALUE! | Begin creating event materials
#VALUE! | Determine AV, tables, chairs, linens, china, small games license etc.
#VALUE! | Finalize guest list
#VALUE! | Request rental quotes, if needed
#VALUE! | Finalize text and design for event materials
NA | Mail "save the date" cards
#VALUE! | Revisit venue to determine preferred room layout, traffic flow, and color themes
#VALUE! | Request food tasting
NA | Update mailing list from any returns on "save the date" mailing. Share updates with Alumni & Advancement
#VALUE! | Hire a florist, if needed/determine centerpieces
#VALUE! | Final approval of invitation
#VALUE! | Notify police if spaces need blocked off
#VALUE! | Send invitations
#VALUE! | Create and maintain RSVP report
#VALUE! | Finalize menu and all rental contracts
#VALUE! | Select/order event giveaways
#VALUE! | Organize RSVP responses
#VALUE! | Once RSVP deadline has passed, make follow-up calls to those who have not responded and courtesy reminder calls to those that will be attending
#VALUE! | Request security, if needed
#VALUE! | Submit work orders
1 Month Plan | Task | Actual Date Completed | Comments
#VALUE! | Finalize programs
#VALUE! | Create Campus Event Briefing, required if President is attending
-14 | Create information for volunteers and staff working event
DAY OF EVENT | Thorough review of event checklist
POST EVENT | Send out personal thank you's
POST EVENT | Solicit feedback from attendees and also from those who weren't able to attend
POST EVENT | Satisfy all contracts and agreements
POST EVENT | Make a list indicating possible areas of improvement you want to remember next time
POST EVENT | Provide Advancement guest list